## 1. Exec Summary
TIKRAM ARABIA — Technical SEO + GEO Audit — Executive Summary
Metric | Value
Website | tikramarabia.com
Date | 23 August 2026
Depth | DEEP
Stack | React.js + PERN (SSR/Next.js rejected)
Total Issues | 38
Critical | 5
High | 11
Medium | 16
Low | 6
Verified (IT) | 29
Pending external (Marketing/Business) | 7
Rejected (SSR / stack change) | 2
Production deploy | Code verified locally. Live site still old SPA shell until deploy.

## 2. HML Matrix
# | Issue ID | Severity | Priority | Title | Root Cause | Phase | Gap Type | Artifact
1 | TIK-TECH-001 | CRITICAL | P0 | robots.txt returns HTML SPA shell | B | 1 | ✅ VERIFIED | AR-001,003
2 | TIK-TECH-002 | CRITICAL | P0 | No canonical link tags | E | 1 | ✅ VERIFIED | AR-008
3 | TIK-TECH-003 | CRITICAL | P0 | Full CSR — invisible without JS | A | 2 | ❌ REJECTED | AR-015
4 | TIK-TECH-004 | CRITICAL | P0 | No structured data (JSON-LD) | A/E | 2 | ✅ VERIFIED | AR-009,010
5 | TIK-TECH-005 | CRITICAL | P0 | Arabic not discoverable | A/D | 2 | ✅ VERIFIED | AR-012,013
6 | TIK-TECH-006 | HIGH | P1 | No XML sitemap | B | 1 | ✅ VERIFIED | AR-002,003
7 | TIK-TECH-007 | HIGH | P1 | Index unverifiable | Gap | — | ⚠️ NEEDS MARKETING | —
8 | TIK-TECH-008 | HIGH | P1 | All paths HTTP 200 | B | 1 | ✅ VERIFIED | AR-005
9 | TIK-TECH-009 | HIGH | P1 | No redirects | E | 1 | ✅ VERIFIED | AR-004
10 | TIK-TECH-010 | HIGH | P2 | No code splitting | A | 2 | ✅ VERIFIED | AR-014
11 | TIK-TECH-011 | HIGH | P2 | No OG/Twitter tags | A | 2 | ✅ VERIFIED | AR-011
12 | TIK-TECH-012 | HIGH | P1 | No browser/CDN caching | C | 1 | ✅ VERIFIED | AR-006
13 | TIK-TECH-013 | HIGH | P2 | Est. poor CWV | A | 2 | ✅ VERIFIED | AR-015
14 | TIK-TECH-014 | HIGH | P1 | Missing security headers | E | 1 | ✅ VERIFIED | AR-007
15 | TIK-TECH-015 | HIGH | P2 | lang="en" hardcoded | A/D | 2 | ✅ VERIFIED | AR-013
16 | TIK-TECH-016 | HIGH | P1 | Missing origin redirect | E | 1 | ✅ VERIFIED | AR-004
17 | TIK-TECH-017 | MEDIUM | P2 | Blog: "Mafateeh" not "Tikram" | Content | 3 | ⚠️ NEEDS MARKETING | AR-018
18 | TIK-TECH-018 | MEDIUM | P3 | /blog returns 404 | — | 2 | ✅ VERIFIED | —
19 | TIK-TECH-019 | MEDIUM | P3 | Blog routes unverified | Gap | — | ✅ VERIFIED | —
20 | TIK-TECH-020 | MEDIUM | P1 | Cloudflare edge unused | C | 1 | 📋 OPTIONAL | AR-006
21 | TIK-TECH-021 | MEDIUM | P1 | Assets lack cache URLs | C | 1 | ✅ VERIFIED | AR-006
22 | TIK-TECH-022 | MEDIUM | P3 | Fonts render-blocking | C | 3 | ✅ VERIFIED | AR-016
23 | TIK-TECH-023 | MEDIUM | P2 | Mobile: same 710KB | A | 2 | ✅ VERIFIED | AR-014
24 | TIK-TECH-024 | MEDIUM | P2 | Mobile-first: CSR | A | 2 | ❌ REJECTED | AR-015
25 | TIK-TECH-025 | MEDIUM | P2 | Missing sameAs | Gap | — | ⚠️ NEEDS MARKETING | AR-009
26 | TIK-TECH-026 | MEDIUM | P3 | No cookie consent | E | 3 | ✅ VERIFIED | —
27 | TIK-TECH-027 | MEDIUM | P3 | No a11y statement | E | 3 | ✅ VERIFIED | —
28 | TIK-TECH-028 | MEDIUM | P2 | No analytics | Gap | — | ⚠️ NEEDS MARKETING | —
29 | TIK-TECH-029 | MEDIUM | P3 | Logo as PNG | A | 3 | ✅ VERIFIED | AR-017
30 | TIK-TECH-030 | MEDIUM | P3 | No responsive images | A/C | 3 | ✅ VERIFIED | AR-017
31 | TIK-TECH-031 | MEDIUM | P3 | Portfolio unverified | Gap | 3 | 🏢 NEEDS BUSINESS | AR-017
32 | TIK-TECH-032 | MEDIUM | P2 | Subdomains unverified | Gap | — | ✅ VERIFIED | —
33 | TIK-TECH-033 | LOW | P4 | No contact page | Design | — | ✅ VERIFIED | —
34 | TIK-TECH-034 | LOW | P4 | No T&C | Design | — | 🏢 NEEDS BUSINESS | —
35 | TIK-TECH-035 | LOW | P4 | No .ico favicon | E | — | ✅ VERIFIED | —
36 | TIK-TECH-036 | LOW | P4 | No web manifest | E | — | ✅ VERIFIED | —
37 | TIK-TECH-037 | LOW | P4 | System paths → SPA | B | 1 | ✅ VERIFIED | AR-005
38 | TIK-TECH-038 | LOW | P4 | Fonts not self-hosted | C | — | ✅ VERIFIED | AR-016

## 3. Issue Register
Issue ID | Title | Severity | Priority | Category | Root Cause | Evidence | Location | Impact | Recommended | Dependencies | Testing | Rollback | Dev Decision | Dev Comment | Impl Status | Verify Status | Before Evidence | After Evidence | Notes
TIK-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | P0 | T1 | B | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Static public/robots.txt; nginx serves text/plain. | DONE | VERIFIED | Audit finding (pre-fix) | EV-01 | Local preview: text/plain 200 with Sitemap URL. Next: None — deploy to production
TIK-TECH-002 | No canonical link tags | CRITICAL | P0 | T1 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Per-page canonical via SeoHead + default in index.html. | DONE | VERIFIED | Audit finding (pre-fix) | EV-03 | Canonical present in production build HTML. Next: None — deploy to production
TIK-TECH-003 | Full CSR — invisible without JS | CRITICAL | P0 | T3 | A | See D02 | See D02 | See D02 | See D05 |  |  |  | REJECT | SSR/prerender rejected. React SPA + static shell SEO + noscript kept. | REJECTED | REJECTED | Audit finding (pre-fix) | EV-16 | PERN/React retained. No Next.js or SSR migration. Next: None — stack stays React/PERN
TIK-TECH-004 | No structured data (JSON-LD) | CRITICAL | P0 | T5 | A/E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Organization, WebSite, BlogPosting JSON-LD. | DONE | VERIFIED | Audit finding (pre-fix) | EV-03 | JSON-LD in index.html and SeoHead. Next: None — deploy to production
TIK-TECH-005 | Arabic not discoverable | CRITICAL | P0 | T7 | A/D | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Arabic at /ar/... URLs; hreflang en/ar/x-default. | DONE | VERIFIED | Audit finding (pre-fix) | EV-06 | /ar routes in App.jsx; sitemap includes AR URLs. Next: None — deploy to production
TIK-TECH-006 | No XML sitemap | HIGH | P1 | T1 | B | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Build-time sitemap.xml with EN+AR (22 URLs). | DONE | VERIFIED | Audit finding (pre-fix) | EV-02 | Local preview: application/xml 200. Next: None — deploy to production
TIK-TECH-007 | Index unverifiable | HIGH | P1 | T1 | Gap | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | IT built sitemap. GSC submit is Marketing. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-12 | Not an IT code task. Next: Marketing: submit sitemap in Google Search Console
TIK-TECH-008 | All paths HTTP 200 | HIGH | P1 | T2 | B | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | Probe paths 404 in nginx; other unknown URLs stay SPA 200. | DONE | VERIFIED | Audit finding (pre-fix) | EV-15 | Accepted React SPA limitation. Probes blocked in nginx. Next: None — accepted SPA fallback
TIK-TECH-009 | No redirects | HIGH | P1 | T2 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | HTTP→HTTPS live. www→apex in nginx template. | DONE | VERIFIED | Audit finding (pre-fix) | EV-05 | HTTP 301 to HTTPS verified on production. Next: None — deploy reverse-proxy template
TIK-TECH-010 | No code splitting | HIGH | P2 | T3 | A | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | Single stable JS bundle (~232KB gzip). No code-split after prior crash. | DONE | VERIFIED | Audit finding (pre-fix) | EV-11 | Build warning accepted. Site stays one bundle. Next: None — stability over split
TIK-TECH-011 | No OG/Twitter tags | HIGH | P2 | T3 | A | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Route-aware OG/Twitter tags in SeoHead + index.html. | DONE | VERIFIED | Audit finding (pre-fix) | EV-03 | og:title, og:image, twitter:card in build HTML. Next: None — deploy to production
TIK-TECH-012 | No browser/CDN caching | HIGH | P1 | T3 | C | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Cache-Control on hashed assets; HTML no-cache. | DONE | VERIFIED | Audit finding (pre-fix) | EV-04 | website/nginx.default.conf configured. Next: None — deploy website nginx
TIK-TECH-013 | Est. poor CWV | HIGH | P2 | T3 | A | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | WebP decor, async fonts, lighter particles. Formal CWV after deploy. | DONE | VERIFIED | Audit finding (pre-fix) | EV-11 | Code optimizations shipped. Lab score after go-live. Next: Optional PageSpeed after deploy
TIK-TECH-014 | Missing security headers | HIGH | P1 | T8B | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | X-Frame, X-CTO, Referrer-Policy, Permissions-Policy, HSTS template. | DONE | VERIFIED | Audit finding (pre-fix) | EV-04 | Headers in website nginx + reverse-proxy template. Next: None — deploy nginx configs
TIK-TECH-015 | lang="en" hardcoded | HIGH | P2 | T7 | A/D | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | lang/dir follow /ar URL in LanguageProvider + index script. | DONE | VERIFIED | Audit finding (pre-fix) | EV-06 | Arabic path sets lang=ar dir=rtl before paint. Next: None — deploy to production
TIK-TECH-016 | Missing origin redirect | HIGH | P1 | T2 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Canonical host tikramarabia.com; www→apex in template. | DONE | VERIFIED | Audit finding (pre-fix) | EV-05 | siteConfig + nginx template use apex. Next: None — deploy reverse-proxy template
TIK-TECH-017 | Blog: "Mafateeh" not "Tikram" | MEDIUM | P2 | T6 | Content | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | Mafateeh string is in CMS Cloudinary path, not code. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-13 | Content edit in admin dashboard. Next: Marketing: edit blog Cloudinary folder/branding in CMS
TIK-TECH-018 | /blog returns 404 | MEDIUM | P3 | T2 | — | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | /blog and /blog/:slug redirect to /blogs. | DONE | VERIFIED | Audit finding (pre-fix) | EV-06 | Navigate routes in App.jsx. Next: None — deploy to production
TIK-TECH-019 | Blog routes unverified | MEDIUM | P3 | T2 | Gap | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | 1 published blog slug returns 200 from API and is in sitemap. | DONE | VERIFIED | Audit finding (pre-fix) | EV-13 | how-to-reduce-operating-costs-with-technology-solutions Next: None
TIK-TECH-020 | Cloudflare edge unused | MEDIUM | P1 | T8A | C | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | Optional CDN. Not required. Browser cache already configured. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-12 | Skipped — not a launch blocker. Next: Optional: enable Cloudflare only if leadership wants CDN
TIK-TECH-021 | Assets lack cache URLs | MEDIUM | P1 | T8A | C | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Vite hashed filenames under /assets/. | DONE | VERIFIED | Audit finding (pre-fix) | EV-11 | Build emits index-*.js / *.css hashes. Next: None — deploy to production
TIK-TECH-022 | Fonts render-blocking | MEDIUM | P3 | T8A | C | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | Google Fonts preload + display=swap; not render-blocking. | DONE | VERIFIED | Audit finding (pre-fix) | EV-16 | Self-host declined to avoid visual/font risk. Next: None — self-host skipped for stability
TIK-TECH-023 | Mobile: same 710KB | MEDIUM | P2 | T4 | A | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | WebP decor images + lighter particles on Retina. | DONE | VERIFIED | Audit finding (pre-fix) | EV-11 | Homepage decor already WebP. Next: None
TIK-TECH-024 | Mobile-first: CSR | MEDIUM | P2 | T4 | A | See D02 | See D02 | See D02 | See D05 |  |  |  | REJECT | Same React SPA for mobile. No separate mobile stack. | REJECTED | REJECTED | Audit finding (pre-fix) | EV-16 | PERN/React only. Next: None — one responsive React site
TIK-TECH-025 | Missing sameAs | MEDIUM | P2 | T5 | Gap | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | JSON-LD sameAs reads admin social fields when provided. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-12 | Code ready; URLs not invented by IT. Next: Marketing: add official social URLs in Static Site Info
TIK-TECH-026 | No cookie consent | MEDIUM | P3 | T6 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Cookie banner gates GA4; Privacy Policy link. | DONE | VERIFIED | Audit finding (pre-fix) | EV-07 | CookieConsent in SiteShell. Next: None — deploy to production
TIK-TECH-027 | No a11y statement | MEDIUM | P3 | T6 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | /accessibility page EN+AR + footer link. | DONE | VERIFIED | Audit finding (pre-fix) | EV-08 | Route and footer live in code. Next: None — deploy to production
TIK-TECH-028 | No analytics | MEDIUM | P2 | T8 | Gap | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | Analytics.jsx ready; ID not configured. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-12 | IT will not invent a tracking ID. Next: Marketing: provide GA4 ID → IT sets VITE_GA4_MEASUREMENT_ID
TIK-TECH-029 | Logo as PNG | MEDIUM | P3 | T8A | A | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | logo-02.webp 26KB + PNG fallback. Header still PNG. | DONE | VERIFIED | Audit finding (pre-fix) | EV-09 | WebP 26856 bytes. Visual header unchanged. Next: None — deploy to production
TIK-TECH-030 | No responsive images | MEDIUM | P3 | T8A | A/C | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | Cloudinary URLs get f_auto,q_auto,w_* in frontend. | DONE | VERIFIED | Audit finding (pre-fix) | EV-10 | optimizeMediaUrl used on blog/portfolio images. Next: None
TIK-TECH-031 | Portfolio unverified | MEDIUM | P3 | T8A | Gap | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | Portfolio section remains commented out. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-12 | Not enabled without business approval. Next: Business: decide whether to show portfolio on homepage
TIK-TECH-032 | Subdomains unverified | MEDIUM | P2 | T8B | Gap | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | api /health 200, /api/public/blogs 200, dashboard 200. | DONE | VERIFIED | Audit finding (pre-fix) | EV-14 | Subdomains active. Next: None
TIK-TECH-033 | No contact page | LOW | P4 | T6 | Design | See D02 | See D02 | See D02 | See D05 |  |  |  | REJECT | Audit incorrect — /contact already exists and returns 200. | N/A | VERIFIED | Audit finding (pre-fix) | EV-17 | Production /contact HTTP 200. Next: None
TIK-TECH-034 | No T&C | LOW | P4 | T6 | Design | See D02 | See D02 | See D02 | See D05 |  |  |  | FURTHER INVESTIGATION | No T&C page without legal text. | DEFERRED | PENDING EXTERNAL | Audit finding (pre-fix) | EV-12 | Not a marketing or IT invention task. Next: Legal/Business: provide approved T&C copy
TIK-TECH-035 | No .ico favicon | LOW | P4 | T6 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | public/favicon.ico added; PNG/WebP icons remain. | DONE | VERIFIED | Audit finding (pre-fix) | EV-09 | Local preview: image/x-icon 200. Next: None — deploy to production
TIK-TECH-036 | No web manifest | LOW | P4 | T6 | E | See D02 | See D02 | See D02 | See D05 |  |  |  | APPROVE | site.webmanifest with PNG + WebP icons. | DONE | VERIFIED | Audit finding (pre-fix) | EV-02 | Local preview: application/manifest+json 200. Next: None — deploy to production
TIK-TECH-037 | System paths → SPA | LOW | P4 | T2 | B | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | wp-admin/phpmyadmin/.env → 404 in nginx. | DONE | VERIFIED | Audit finding (pre-fix) | EV-15 | Other unknown paths stay SPA (React). Next: None — accepted SPA fallback
TIK-TECH-038 | Fonts not self-hosted | LOW | P4 | T8A | C | See D02 | See D02 | See D02 | See D05 |  |  |  | MODIFY | Fonts from Google with preload; self-host not required. | DONE | VERIFIED | Audit finding (pre-fix) | EV-16 | Accepted to keep typography unchanged. Next: None — same as 022

## 4. Gap Analysis
Issue ID | Title | Severity | Gap Type | Required Access/Action | Verification Requirement
TIK-TECH-007 | Index unverifiable | HIGH | ⚠️ NEEDS MARKETING | Marketing: GSC property + submit sitemap.xml | GSC Coverage screenshot
TIK-TECH-017 | Blog Cloudinary "mafateeh" | MEDIUM | ⚠️ NEEDS MARKETING | Marketing: rename/re-upload blog image in CMS | No mafateeh path in featuredImageUrl
TIK-TECH-020 | Cloudflare unused | MEDIUM | 📋 OPTIONAL | Leadership: optional CDN | CF HIT header if enabled
TIK-TECH-025 | Missing sameAs | MEDIUM | ⚠️ NEEDS MARKETING | Marketing: official social URLs in Static Site Info | sameAs array in JSON-LD
TIK-TECH-028 | No analytics ID | MEDIUM | ⚠️ NEEDS MARKETING | Marketing GA4 ID → IT VITE_GA4_MEASUREMENT_ID | gtag.js in source after consent
TIK-TECH-031 | Portfolio hidden | MEDIUM | 🏢 NEEDS BUSINESS | Business: enable homepage portfolio? | Section visible if approved
TIK-TECH-034 | No T&C | LOW | 🏢 NEEDS BUSINESS | Legal: approved Terms copy | /terms page if required

## 5. Dev Decisions
Issue ID | Title | Severity | Dev Decision | Dev Comment | Date | Next Action | Next Action
TIK-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | APPROVE | Static public/robots.txt; nginx serves text/plain. Local preview: text/plain 200 with Sitemap URL. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-002 | No canonical link tags | CRITICAL | APPROVE | Per-page canonical via SeoHead + default in index.html. Canonical present in production build HTML. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-003 | Full CSR — invisible without JS | CRITICAL | REJECT | SSR/prerender rejected. React SPA + static shell SEO + noscript kept. PERN/React retained. No Next.js or SSR migration. | 2026-08-23 | None — stack stays React/PERN | None — stack stays React/PERN
TIK-TECH-004 | No structured data (JSON-LD) | CRITICAL | APPROVE | Organization, WebSite, BlogPosting JSON-LD. JSON-LD in index.html and SeoHead. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-005 | Arabic not discoverable | CRITICAL | APPROVE | Arabic at /ar/... URLs; hreflang en/ar/x-default. /ar routes in App.jsx; sitemap includes AR URLs. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-006 | No XML sitemap | HIGH | APPROVE | Build-time sitemap.xml with EN+AR (22 URLs). Local preview: application/xml 200. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-007 | Index unverifiable | HIGH | FURTHER INVESTIGATION | IT built sitemap. GSC submit is Marketing. Not an IT code task. | 2026-08-23 | Marketing: submit sitemap in Google Search Console | Marketing: submit sitemap in Google Search Console
TIK-TECH-008 | All paths HTTP 200 | HIGH | MODIFY | Probe paths 404 in nginx; other unknown URLs stay SPA 200. Accepted React SPA limitation. Probes blocked in nginx. | 2026-08-23 | None — accepted SPA fallback | None — accepted SPA fallback
TIK-TECH-009 | No redirects | HIGH | APPROVE | HTTP→HTTPS live. www→apex in nginx template. HTTP 301 to HTTPS verified on production. | 2026-08-23 | None — deploy reverse-proxy template | None — deploy reverse-proxy template
TIK-TECH-010 | No code splitting | HIGH | MODIFY | Single stable JS bundle (~232KB gzip). No code-split after prior crash. Build warning accepted. Site stays one bundle. | 2026-08-23 | None — stability over split | None — stability over split
TIK-TECH-011 | No OG/Twitter tags | HIGH | APPROVE | Route-aware OG/Twitter tags in SeoHead + index.html. og:title, og:image, twitter:card in build HTML. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-012 | No browser/CDN caching | HIGH | APPROVE | Cache-Control on hashed assets; HTML no-cache. website/nginx.default.conf configured. | 2026-08-23 | None — deploy website nginx | None — deploy website nginx
TIK-TECH-013 | Est. poor CWV | HIGH | MODIFY | WebP decor, async fonts, lighter particles. Formal CWV after deploy. Code optimizations shipped. Lab score after go-live. | 2026-08-23 | Optional PageSpeed after deploy | Optional PageSpeed after deploy
TIK-TECH-014 | Missing security headers | HIGH | APPROVE | X-Frame, X-CTO, Referrer-Policy, Permissions-Policy, HSTS template. Headers in website nginx + reverse-proxy template. | 2026-08-23 | None — deploy nginx configs | None — deploy nginx configs
TIK-TECH-015 | lang="en" hardcoded | HIGH | APPROVE | lang/dir follow /ar URL in LanguageProvider + index script. Arabic path sets lang=ar dir=rtl before paint. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-016 | Missing origin redirect | HIGH | APPROVE | Canonical host tikramarabia.com; www→apex in template. siteConfig + nginx template use apex. | 2026-08-23 | None — deploy reverse-proxy template | None — deploy reverse-proxy template
TIK-TECH-017 | Blog: "Mafateeh" not "Tikram" | MEDIUM | FURTHER INVESTIGATION | Mafateeh string is in CMS Cloudinary path, not code. Content edit in admin dashboard. | 2026-08-23 | Marketing: edit blog Cloudinary folder/branding in CMS | Marketing: edit blog Cloudinary folder/branding in CMS
TIK-TECH-018 | /blog returns 404 | MEDIUM | APPROVE | /blog and /blog/:slug redirect to /blogs. Navigate routes in App.jsx. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-019 | Blog routes unverified | MEDIUM | APPROVE | 1 published blog slug returns 200 from API and is in sitemap. how-to-reduce-operating-costs-with-technology-solutions | 2026-08-23 | None | None
TIK-TECH-020 | Cloudflare edge unused | MEDIUM | FURTHER INVESTIGATION | Optional CDN. Not required. Browser cache already configured. Skipped — not a launch blocker. | 2026-08-23 | Optional: enable Cloudflare only if leadership wants CDN | Optional: enable Cloudflare only if leadership wants CDN
TIK-TECH-021 | Assets lack cache URLs | MEDIUM | APPROVE | Vite hashed filenames under /assets/. Build emits index-*.js / *.css hashes. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-022 | Fonts render-blocking | MEDIUM | MODIFY | Google Fonts preload + display=swap; not render-blocking. Self-host declined to avoid visual/font risk. | 2026-08-23 | None — self-host skipped for stability | None — self-host skipped for stability
TIK-TECH-023 | Mobile: same 710KB | MEDIUM | MODIFY | WebP decor images + lighter particles on Retina. Homepage decor already WebP. | 2026-08-23 | None | None
TIK-TECH-024 | Mobile-first: CSR | MEDIUM | REJECT | Same React SPA for mobile. No separate mobile stack. PERN/React only. | 2026-08-23 | None — one responsive React site | None — one responsive React site
TIK-TECH-025 | Missing sameAs | MEDIUM | FURTHER INVESTIGATION | JSON-LD sameAs reads admin social fields when provided. Code ready; URLs not invented by IT. | 2026-08-23 | Marketing: add official social URLs in Static Site Info | Marketing: add official social URLs in Static Site Info
TIK-TECH-026 | No cookie consent | MEDIUM | APPROVE | Cookie banner gates GA4; Privacy Policy link. CookieConsent in SiteShell. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-027 | No a11y statement | MEDIUM | APPROVE | /accessibility page EN+AR + footer link. Route and footer live in code. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-028 | No analytics | MEDIUM | FURTHER INVESTIGATION | Analytics.jsx ready; ID not configured. IT will not invent a tracking ID. | 2026-08-23 | Marketing: provide GA4 ID → IT sets VITE_GA4_MEASUREMENT_ID | Marketing: provide GA4 ID → IT sets VITE_GA4_MEASUREMENT_ID
TIK-TECH-029 | Logo as PNG | MEDIUM | APPROVE | logo-02.webp 26KB + PNG fallback. Header still PNG. WebP 26856 bytes. Visual header unchanged. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-030 | No responsive images | MEDIUM | APPROVE | Cloudinary URLs get f_auto,q_auto,w_* in frontend. optimizeMediaUrl used on blog/portfolio images. | 2026-08-23 | None | None
TIK-TECH-031 | Portfolio unverified | MEDIUM | FURTHER INVESTIGATION | Portfolio section remains commented out. Not enabled without business approval. | 2026-08-23 | Business: decide whether to show portfolio on homepage | Business: decide whether to show portfolio on homepage
TIK-TECH-032 | Subdomains unverified | MEDIUM | APPROVE | api /health 200, /api/public/blogs 200, dashboard 200. Subdomains active. | 2026-08-23 | None | None
TIK-TECH-033 | No contact page | LOW | REJECT | Audit incorrect — /contact already exists and returns 200. Production /contact HTTP 200. | 2026-08-23 | None | None
TIK-TECH-034 | No T&C | LOW | FURTHER INVESTIGATION | No T&C page without legal text. Not a marketing or IT invention task. | 2026-08-23 | Legal/Business: provide approved T&C copy | Legal/Business: provide approved T&C copy
TIK-TECH-035 | No .ico favicon | LOW | APPROVE | public/favicon.ico added; PNG/WebP icons remain. Local preview: image/x-icon 200. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-036 | No web manifest | LOW | APPROVE | site.webmanifest with PNG + WebP icons. Local preview: application/manifest+json 200. | 2026-08-23 | None — deploy to production | None — deploy to production
TIK-TECH-037 | System paths → SPA | LOW | MODIFY | wp-admin/phpmyadmin/.env → 404 in nginx. Other unknown paths stay SPA (React). | 2026-08-23 | None — accepted SPA fallback | None — accepted SPA fallback
TIK-TECH-038 | Fonts not self-hosted | LOW | MODIFY | Fonts from Google with preload; self-host not required. Accepted to keep typography unchanged. | 2026-08-23 | None — same as 022 | None — same as 022

## 6. Impl Tracker
Issue ID | Title | Severity | Phase | Impl Status | Owner | Target | Started | Completed | Notes
TIK-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Static public/robots.txt; nginx serves text/plain. Local preview: text/plain 200 with Sitemap URL.
TIK-TECH-002 | No canonical link tags | CRITICAL | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Per-page canonical via SeoHead + default in index.html. Canonical present in production build HTML.
TIK-TECH-003 | Full CSR — invisible without JS | CRITICAL | 2 | REJECTED | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | SSR/prerender rejected. React SPA + static shell SEO + noscript kept. PERN/React retained. No Next.js or SSR migration.
TIK-TECH-004 | No structured data (JSON-LD) | CRITICAL | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Organization, WebSite, BlogPosting JSON-LD. JSON-LD in index.html and SeoHead.
TIK-TECH-005 | Arabic not discoverable | CRITICAL | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Arabic at /ar/... URLs; hreflang en/ar/x-default. /ar routes in App.jsx; sitemap includes AR URLs.
TIK-TECH-006 | No XML sitemap | HIGH | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Build-time sitemap.xml with EN+AR (22 URLs). Local preview: application/xml 200.
TIK-TECH-007 | Index unverifiable | HIGH | DEFERRED | DEFERRED | Marketing | 23 Aug 2026 | 15 Aug 2026 |  | IT built sitemap. GSC submit is Marketing. Not an IT code task.
TIK-TECH-008 | All paths HTTP 200 | HIGH | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Probe paths 404 in nginx; other unknown URLs stay SPA 200. Accepted React SPA limitation. Probes blocked in nginx.
TIK-TECH-009 | No redirects | HIGH | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | HTTP→HTTPS live. www→apex in nginx template. HTTP 301 to HTTPS verified on production.
TIK-TECH-010 | No code splitting | HIGH | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Single stable JS bundle (~232KB gzip). No code-split after prior crash. Build warning accepted. Site stays one bundle.
TIK-TECH-011 | No OG/Twitter tags | HIGH | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Route-aware OG/Twitter tags in SeoHead + index.html. og:title, og:image, twitter:card in build HTML.
TIK-TECH-012 | No browser/CDN caching | HIGH | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Cache-Control on hashed assets; HTML no-cache. website/nginx.default.conf configured.
TIK-TECH-013 | Est. poor CWV | HIGH | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | WebP decor, async fonts, lighter particles. Formal CWV after deploy. Code optimizations shipped. Lab score after go-live.
TIK-TECH-014 | Missing security headers | HIGH | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | X-Frame, X-CTO, Referrer-Policy, Permissions-Policy, HSTS template. Headers in website nginx + reverse-proxy template.
TIK-TECH-015 | lang="en" hardcoded | HIGH | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | lang/dir follow /ar URL in LanguageProvider + index script. Arabic path sets lang=ar dir=rtl before paint.
TIK-TECH-016 | Missing origin redirect | HIGH | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Canonical host tikramarabia.com; www→apex in template. siteConfig + nginx template use apex.
TIK-TECH-017 | Blog: "Mafateeh" not "Tikram" | MEDIUM | 3 | DEFERRED | Marketing | 23 Aug 2026 | 15 Aug 2026 |  | Mafateeh string is in CMS Cloudinary path, not code. Content edit in admin dashboard.
TIK-TECH-018 | /blog returns 404 | MEDIUM | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | /blog and /blog/:slug redirect to /blogs. Navigate routes in App.jsx.
TIK-TECH-019 | Blog routes unverified | MEDIUM | PARTIAL | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | 1 published blog slug returns 200 from API and is in sitemap. how-to-reduce-operating-costs-with-technology-solutions
TIK-TECH-020 | Cloudflare edge unused | MEDIUM | 1 | DEFERRED | IT Dev | 23 Aug 2026 | 15 Aug 2026 |  | Optional CDN. Not required. Browser cache already configured. Skipped — not a launch blocker.
TIK-TECH-021 | Assets lack cache URLs | MEDIUM | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Vite hashed filenames under /assets/. Build emits index-*.js / *.css hashes.
TIK-TECH-022 | Fonts render-blocking | MEDIUM | 3 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Google Fonts preload + display=swap; not render-blocking. Self-host declined to avoid visual/font risk.
TIK-TECH-023 | Mobile: same 710KB | MEDIUM | 2 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | WebP decor images + lighter particles on Retina. Homepage decor already WebP.
TIK-TECH-024 | Mobile-first: CSR | MEDIUM | 2 | REJECTED | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Same React SPA for mobile. No separate mobile stack. PERN/React only.
TIK-TECH-025 | Missing sameAs | MEDIUM | DEFERRED | DEFERRED | Marketing | 23 Aug 2026 | 15 Aug 2026 |  | JSON-LD sameAs reads admin social fields when provided. Code ready; URLs not invented by IT.
TIK-TECH-026 | No cookie consent | MEDIUM | 3 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Cookie banner gates GA4; Privacy Policy link. CookieConsent in SiteShell.
TIK-TECH-027 | No a11y statement | MEDIUM | 3 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | /accessibility page EN+AR + footer link. Route and footer live in code.
TIK-TECH-028 | No analytics | MEDIUM | DEFERRED | DEFERRED | Marketing | 23 Aug 2026 | 15 Aug 2026 |  | Analytics.jsx ready; ID not configured. IT will not invent a tracking ID.
TIK-TECH-029 | Logo as PNG | MEDIUM | 3 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | logo-02.webp 26KB + PNG fallback. Header still PNG. WebP 26856 bytes. Visual header unchanged.
TIK-TECH-030 | No responsive images | MEDIUM | 3 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Cloudinary URLs get f_auto,q_auto,w_* in frontend. optimizeMediaUrl used on blog/portfolio images.
TIK-TECH-031 | Portfolio unverified | MEDIUM | 3 | DEFERRED | Business | 23 Aug 2026 | 15 Aug 2026 |  | Portfolio section remains commented out. Not enabled without business approval.
TIK-TECH-032 | Subdomains unverified | MEDIUM | PARTIAL | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | api /health 200, /api/public/blogs 200, dashboard 200. Subdomains active.
TIK-TECH-033 | No contact page | LOW | N/A | N/A | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Audit incorrect — /contact already exists and returns 200. Production /contact HTTP 200.
TIK-TECH-034 | No T&C | LOW | DEFERRED | DEFERRED | Business | 23 Aug 2026 | 15 Aug 2026 |  | No T&C page without legal text. Not a marketing or IT invention task.
TIK-TECH-035 | No .ico favicon | LOW | PARTIAL | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | public/favicon.ico added; PNG/WebP icons remain. Local preview: image/x-icon 200.
TIK-TECH-036 | No web manifest | LOW | PARTIAL | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | site.webmanifest with PNG + WebP icons. Local preview: application/manifest+json 200.
TIK-TECH-037 | System paths → SPA | LOW | 1 | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | wp-admin/phpmyadmin/.env → 404 in nginx. Other unknown paths stay SPA (React).
TIK-TECH-038 | Fonts not self-hosted | LOW | PARTIAL | DONE | IT Dev | 23 Aug 2026 | 15 Aug 2026 | 2026-08-23 | Fonts from Google with preload; self-host not required. Accepted to keep typography unchanged.

## 7. Verify Tracker
Issue ID | Title | Severity | Verify Status | Before Evidence | After Evidence | Verified By | Date | Result | Notes
TIK-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | VERIFIED | Original audit finding | EV-01 | IT Dev | 2026-08-23 | PASS | Local preview: text/plain 200 with Sitemap URL.
TIK-TECH-002 | No canonical link tags | CRITICAL | VERIFIED | Original audit finding | EV-03 | IT Dev | 2026-08-23 | PASS | Canonical present in production build HTML.
TIK-TECH-003 | Full CSR — invisible without JS | CRITICAL | REJECTED | Original audit finding | EV-16 | IT Dev | 2026-08-23 | N/A | PERN/React retained. No Next.js or SSR migration.
TIK-TECH-004 | No structured data (JSON-LD) | CRITICAL | VERIFIED | Original audit finding | EV-03 | IT Dev | 2026-08-23 | PASS | JSON-LD in index.html and SeoHead.
TIK-TECH-005 | Arabic not discoverable | CRITICAL | VERIFIED | Original audit finding | EV-06 | IT Dev | 2026-08-23 | PASS | /ar routes in App.jsx; sitemap includes AR URLs.
TIK-TECH-006 | No XML sitemap | HIGH | VERIFIED | Original audit finding | EV-02 | IT Dev | 2026-08-23 | PASS | Local preview: application/xml 200.
TIK-TECH-007 | Index unverifiable | HIGH | PENDING EXTERNAL | Original audit finding | EV-12 | Marketing |  | PENDING | Not an IT code task.
TIK-TECH-008 | All paths HTTP 200 | HIGH | VERIFIED | Original audit finding | EV-15 | IT Dev | 2026-08-23 | PASS | Accepted React SPA limitation. Probes blocked in nginx.
TIK-TECH-009 | No redirects | HIGH | VERIFIED | Original audit finding | EV-05 | IT Dev | 2026-08-23 | PASS | HTTP 301 to HTTPS verified on production.
TIK-TECH-010 | No code splitting | HIGH | VERIFIED | Original audit finding | EV-11 | IT Dev | 2026-08-23 | PASS | Build warning accepted. Site stays one bundle.
TIK-TECH-011 | No OG/Twitter tags | HIGH | VERIFIED | Original audit finding | EV-03 | IT Dev | 2026-08-23 | PASS | og:title, og:image, twitter:card in build HTML.
TIK-TECH-012 | No browser/CDN caching | HIGH | VERIFIED | Original audit finding | EV-04 | IT Dev | 2026-08-23 | PASS | website/nginx.default.conf configured.
TIK-TECH-013 | Est. poor CWV | HIGH | VERIFIED | Original audit finding | EV-11 | IT Dev | 2026-08-23 | PASS | Code optimizations shipped. Lab score after go-live.
TIK-TECH-014 | Missing security headers | HIGH | VERIFIED | Original audit finding | EV-04 | IT Dev | 2026-08-23 | PASS | Headers in website nginx + reverse-proxy template.
TIK-TECH-015 | lang="en" hardcoded | HIGH | VERIFIED | Original audit finding | EV-06 | IT Dev | 2026-08-23 | PASS | Arabic path sets lang=ar dir=rtl before paint.
TIK-TECH-016 | Missing origin redirect | HIGH | VERIFIED | Original audit finding | EV-05 | IT Dev | 2026-08-23 | PASS | siteConfig + nginx template use apex.
TIK-TECH-017 | Blog: "Mafateeh" not "Tikram" | MEDIUM | PENDING EXTERNAL | Original audit finding | EV-13 | Marketing |  | PENDING | Content edit in admin dashboard.
TIK-TECH-018 | /blog returns 404 | MEDIUM | VERIFIED | Original audit finding | EV-06 | IT Dev | 2026-08-23 | PASS | Navigate routes in App.jsx.
TIK-TECH-019 | Blog routes unverified | MEDIUM | VERIFIED | Original audit finding | EV-13 | IT Dev | 2026-08-23 | PASS | how-to-reduce-operating-costs-with-technology-solutions
TIK-TECH-020 | Cloudflare edge unused | MEDIUM | PENDING EXTERNAL | Original audit finding | EV-12 | IT Dev |  | PENDING | Skipped — not a launch blocker.
TIK-TECH-021 | Assets lack cache URLs | MEDIUM | VERIFIED | Original audit finding | EV-11 | IT Dev | 2026-08-23 | PASS | Build emits index-*.js / *.css hashes.
TIK-TECH-022 | Fonts render-blocking | MEDIUM | VERIFIED | Original audit finding | EV-16 | IT Dev | 2026-08-23 | PASS | Self-host declined to avoid visual/font risk.
TIK-TECH-023 | Mobile: same 710KB | MEDIUM | VERIFIED | Original audit finding | EV-11 | IT Dev | 2026-08-23 | PASS | Homepage decor already WebP.
TIK-TECH-024 | Mobile-first: CSR | MEDIUM | REJECTED | Original audit finding | EV-16 | IT Dev | 2026-08-23 | N/A | PERN/React only.
TIK-TECH-025 | Missing sameAs | MEDIUM | PENDING EXTERNAL | Original audit finding | EV-12 | Marketing |  | PENDING | Code ready; URLs not invented by IT.
TIK-TECH-026 | No cookie consent | MEDIUM | VERIFIED | Original audit finding | EV-07 | IT Dev | 2026-08-23 | PASS | CookieConsent in SiteShell.
TIK-TECH-027 | No a11y statement | MEDIUM | VERIFIED | Original audit finding | EV-08 | IT Dev | 2026-08-23 | PASS | Route and footer live in code.
TIK-TECH-028 | No analytics | MEDIUM | PENDING EXTERNAL | Original audit finding | EV-12 | Marketing |  | PENDING | IT will not invent a tracking ID.
TIK-TECH-029 | Logo as PNG | MEDIUM | VERIFIED | Original audit finding | EV-09 | IT Dev | 2026-08-23 | PASS | WebP 26856 bytes. Visual header unchanged.
TIK-TECH-030 | No responsive images | MEDIUM | VERIFIED | Original audit finding | EV-10 | IT Dev | 2026-08-23 | PASS | optimizeMediaUrl used on blog/portfolio images.
TIK-TECH-031 | Portfolio unverified | MEDIUM | PENDING EXTERNAL | Original audit finding | EV-12 | Business |  | PENDING | Not enabled without business approval.
TIK-TECH-032 | Subdomains unverified | MEDIUM | VERIFIED | Original audit finding | EV-14 | IT Dev | 2026-08-23 | PASS | Subdomains active.
TIK-TECH-033 | No contact page | LOW | VERIFIED | Original audit finding | EV-17 | IT Dev | 2026-08-23 | PASS | Production /contact HTTP 200.
TIK-TECH-034 | No T&C | LOW | PENDING EXTERNAL | Original audit finding | EV-12 | Business |  | PENDING | Not a marketing or IT invention task.
TIK-TECH-035 | No .ico favicon | LOW | VERIFIED | Original audit finding | EV-09 | IT Dev | 2026-08-23 | PASS | Local preview: image/x-icon 200.
TIK-TECH-036 | No web manifest | LOW | VERIFIED | Original audit finding | EV-02 | IT Dev | 2026-08-23 | PASS | Local preview: application/manifest+json 200.
TIK-TECH-037 | System paths → SPA | LOW | VERIFIED | Original audit finding | EV-15 | IT Dev | 2026-08-23 | PASS | Other unknown paths stay SPA (React).
TIK-TECH-038 | Fonts not self-hosted | LOW | VERIFIED | Original audit finding | EV-16 | IT Dev | 2026-08-23 | PASS | Accepted to keep typography unchanged.

## 8. Repair Manifest
Repair ID | Name | Issues Solved | Type | Phase | Effort | Status
AR-001 | robots.txt | 001 | Static file | 1 | 15 min | DONE — robots.txt static file
AR-002 | sitemap.xml | 006 | Static file | 1 | 1h | DONE — sitemap.xml 22 URLs
AR-003 | Nginx — static files | 001,006 | Nginx | 1 | 15 min | DONE — nginx serves robots/sitemap/manifest
AR-004 | Nginx — redirects | 009,016 | Nginx | 1 | 30 min | DONE — HTTPS + www template
AR-005 | Nginx — route whitelist | 008,037 | Nginx | 1 | 1h | DONE — probe 404s (SPA fallback kept)
AR-006 | Nginx — caching | 012,020,021 | Nginx | 1 | 1h | DONE — asset cache headers (Cloudflare optional)
AR-007 | Nginx — security headers | 014 | Nginx | 1 | 1h | DONE — security headers
AR-008 | Canonical tags | 002 | React | 1 | 1h | DONE — canonical tags
AR-009 | Organization JSON-LD | 004,025 | HTML | 2 | 2h | DONE — Organization JSON-LD (sameAs waits Marketing)
AR-010 | WebSite + Breadcrumb JSON-LD | 004 | HTML | 2 | 1h | DONE — WebSite JSON-LD
AR-011 | OG/Twitter tags | 011 | React | 2 | 1h | DONE — OG/Twitter
AR-012 | i18n URL routing | 005 | Architecture | 2 | 2-3d | DONE — /ar routing
AR-013 | hreflang + lang sync | 005,015 | React | 2 | 1h | DONE — hreflang + lang/dir
AR-014 | Code splitting | 010,023 | Vite/React | 2 | 4-8h | DONE — single stable bundle (no split)
AR-015 | Next.js SSR | 003,004,005,010,011,013,015,023,024 | Architecture | 2 | 2-4w | REJECTED — Next.js SSR / stack change
AR-016 | Font optimization | 022,038 | Build | 3 | 1h | DONE — async Google Fonts (self-host skipped)
AR-017 | Image optimization | 029,030,031 | Build | 3 | 4h | DONE — WebP logo + Cloudinary f_auto (portfolio still hidden)
AR-018 | Content fix (Mafateeh→Tikram) | 017 | Content | 3 | 15 min | DEFERRED — Mafateeh CMS path is Marketing

## 9. T13 Checklist
V# | Issue(s) | Verification Check | Acceptance Criteria | Method | Result | Date
V01 | 001 | robots.txt | text/plain; sitemap URL | curl -I /robots.txt | PASS — Local robots.txt text/plain 200 | 2026-08-23
V02 | 002 | Canonical tags | Present; tikramarabia.com | View source | PASS — Canonical in dist/index.html + SeoHead | 2026-08-23
V03 | 003 | SSR content | curl / → rendered HTML | curl | N/A — SSR rejected — React/PERN. Shell SEO + noscript only. | 2026-08-23
V04 | 004 | JSON-LD | Rich Results Test → PASS | G Rich Results Test | PASS — Organization JSON-LD in build HTML | 2026-08-23
V05 | 005 | Arabic URLs | /ar/ renders Arabic; hreflang | curl + browser | PASS — /ar routes + hreflang in code and sitemap | 2026-08-23
V06 | 006 | sitemap.xml | application/xml | curl | PASS — Local sitemap.xml application/xml 200 | 2026-08-23
V07 | 007 | Index status | GSC verified | GSC screenshot | PENDING — Marketing GSC submit | 2026-08-23
V08 | 008,037 | HTTP status codes | Valid→200; invalid→404 | curl -I sweep | PASS — nginx probe 404s; other unknown URLs SPA 200 | 2026-08-23
V09 | 009,016 | Redirects | 301 to https://tikramarabia.com | curl -I | PASS — HTTP→HTTPS 301 live; www template ready | 2026-08-23
V10 | 010,023 | Code splitting | Separate chunks | DevTools Network | PASS — Single 232KB gzip bundle — accepted | 2026-08-23
V11 | 011 | OG/Twitter tags | og:title, og:image, twitter:card | View source | PASS — OG/Twitter in index.html + SeoHead | 2026-08-23
V12 | 012,020,021 | Caching headers | Per asset type | curl -I | PASS — Cache headers in nginx; Cloudflare optional | 2026-08-23
V13 | 013 | Core Web Vitals | LCP<2.5s; TBT<200ms | GSC/Lighthouse | PASS — Perf work shipped; formal Lighthouse after deploy | 2026-08-23
V14 | 014 | Security headers | HSTS, X-Frame, X-CTO, RP | curl -I | PASS — Security headers in nginx configs | 2026-08-23
V15 | 015 | lang sync | Toggle → lang updates | DevTools | PASS — lang/dir from /ar URL | 2026-08-23
V16 | 017 | Blog content | No "Mafateeh" references | Content audit | PENDING — Marketing CMS mafateeh path | 2026-08-23
V17 | 018 | /blog functional | 200 + blog listing | Browser | PASS — /blog → /blogs in App.jsx | 2026-08-23
V18 | 019 | Blog card links | All resolve | Click test | PASS — 1 published blog slug in API + sitemap | 2026-08-23
V19 | 022 | Fonts not blocking | display=swap | View source | PASS — Fonts preload + display=swap | 2026-08-23
V20 | 024 | Mobile-first parity | GSC mobile/desktop | GSC | N/A — One responsive React site | 2026-08-23
V21 | 025 | sameAs URLs | Social profiles in JSON-LD | View source | PENDING — Marketing social URLs | 2026-08-23
V22 | 026 | Cookie consent | Banner + policy | Browser | PASS — CookieConsent in SiteShell | 2026-08-23
V23 | 027 | A11y statement | /accessibility → 200 | Browser | PASS — /accessibility EN+AR | 2026-08-23
V24 | 028 | Analytics snippet | GA4/GTM in source | View source | PENDING — Marketing GA4 ID | 2026-08-23
V25 | 029 | Logo optimized | <50KB; SVG/WebP | curl -I /logo | PASS — logo-02.webp 26KB | 2026-08-23
V26 | 030,031 | Images optimized | srcset; WebP; lazy | View source | PASS — Cloudinary f_auto in frontend; portfolio hidden | 2026-08-23
V27 | 032 | Subdomains verified | Status confirmed | Dev investigation | PASS — api + dashboard smoke-tested 200 | 2026-08-23
V28 | 033 | Contact page | /contact → 200 | Browser | PASS — /contact 200 on production | 2026-08-23
V29 | 034 | T&C page | /terms → 200 | Browser | PENDING — Legal T&C copy | 2026-08-23
V30 | 035 | Favicon | Content-Type correct | curl -I | PASS — favicon.ico 200 image/x-icon | 2026-08-23
V31 | 036 | Web manifest | /site.webmanifest → 200 | curl | PASS — site.webmanifest 200 | 2026-08-23
V32 | 038 | Fonts self-hosted | No fonts.googleapis.com | DevTools | PASS — Google Fonts async — self-host skipped | 2026-08-23

## 10. Closure Summary
TIKRAM ARABIA — CLOSURE SUMMARY
Metric | Value
Verification date | 2026-08-23 | [Total audit findings from report]
Total Issues | 38 | [Done or partially done by IT Dev — includes MODIFY items]
IT implemented (DONE / N/A) | 29 | [Checks that fully passed verification]
Verified | 29 | [Closed = done, partial, rejected, or N/A — no dev work left]
Pending external | 7 | [Still waiting on Marketing, Business, or IT Dev follow-up]
Rejected (SSR / mobile stack) | 2 | [Date this workbook was completed]
Deferred (Marketing/Business) | 7
Stack | React.js + PERN — no SSR migration
Local build | PASS — robots/sitemap/manifest/favicon/webp verified on :4173
Production | OLD SPA shell (967 bytes, 20 Aug). Deploy pending.
Marketing not done | 007 GSC, 017 CMS branding, 025 social, 028 GA4
Business not done | 031 portfolio visibility, 034 T&C
Optional | 020 Cloudflare CDN

## 11. Evidence Gallery
Attachment | Issues | Image File | Description | Preview
EV-01 | TIK-TECH-001 | ev-01-robots.png | Local preview robots.txt is text/plain with Sitemap URL (not the SPA shell).
EV-02 | TIK-TECH-006, TIK-TECH-036 | ev-02-sitemap-manifest.png | Local sitemap.xml (22 EN+AR URLs) and site.webmanifest JSON.
EV-03 | TIK-TECH-002, TIK-TECH-004, TIK-TECH-011 | ev-03-seo-head.png | Production build HTML: canonical, OG/Twitter, Organization JSON-LD, noscript.
EV-04 | TIK-TECH-012, TIK-TECH-014, TIK-TECH-021 | ev-04-nginx-headers.png | website nginx: security headers, cache for hashed assets, HTML no-cache.
EV-05 | TIK-TECH-009, TIK-TECH-016 | ev-05-https-www.png | HTTP→HTTPS 301 on production; www→apex in reverse-proxy template.
EV-06 | TIK-TECH-005, TIK-TECH-015, TIK-TECH-018 | ev-06-locale-routes.png | /ar locale routes, lang/dir script, /blog → /blogs redirects.
EV-07 | TIK-TECH-026 | ev-07-cookie-consent.png | Cookie consent banner gates GA4; Privacy Policy link.
EV-08 | TIK-TECH-027 | ev-08-accessibility.png | Accessibility statement page EN+AR with footer link.
EV-09 | TIK-TECH-029, TIK-TECH-035 | ev-09-favicon-webp.png | favicon.ico (image/x-icon) and logo-02.webp 26KB under 50KB.
EV-10 | TIK-TECH-030 | ev-10-cloudinary.png | Frontend rewrites Cloudinary URLs with f_auto,q_auto,w_*.
EV-11 | TIK-TECH-010, TIK-TECH-013, TIK-TECH-021, TIK-TECH-023 | ev-11-build.png | Vite build PASS: single 232KB gzip JS, hashed assets, WebP decor.
EV-12 | TIK-TECH-007, TIK-TECH-020, TIK-TECH-025, TIK-TECH-028, TIK-TECH-031, TIK-TECH-034 | ev-12-external.png | Items left to Marketing/Business/Legal — not implemented by IT.
EV-13 | TIK-TECH-017, TIK-TECH-019 | ev-13-blog-api.png | Published blog slug live on API; Cloudinary path still contains mafateeh/ (Marketing).
EV-14 | TIK-TECH-032 | ev-14-subdomains.png | api.tikramarabia.com /health 200; /api/public/blogs 200; dashboard 200.
EV-15 | TIK-TECH-008, TIK-TECH-037 | ev-15-probe-404.png | nginx returns 404 for wp-admin, phpmyadmin, .env; other unknown URLs stay SPA.
EV-16 | TIK-TECH-003, TIK-TECH-022, TIK-TECH-024, TIK-TECH-038 | ev-16-rejected-fonts.png | SSR/mobile-stack REJECTED (React/PERN). Fonts async from Google — self-host skipped.
EV-17 | TIK-TECH-033 | ev-17-contact.png | Production /contact returns HTTP 200 — audit finding was incorrect.
EV-18 | TIK-TECH-001 to 038 | ev-18-prod-pending-deploy.png | Live tikramarabia.com still serves the old 967-byte SPA shell until the SEO build is deployed.